## VO1
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 13/08/2025
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO1 - Wet Fire Variation to Ground Floor
Item | Description |  |  |  | Cost | Credit
| Additional works from Design to IFC Drawings from Forth Engineering | Qty | Unit | Rate ($)
1 | Relocation of Fire Hydrant - additional Hydrant and Enclosure | 1 | item | 31345 | 31345
2 | Additional pipework and sleeves as per IFC drawings | 1 | item | 15678 | 15678
3 | Earthwork allowance - detail excavation, refill and for additional works | 1 | item | 9860 | 9860
4 | 600x600x600mm concrete pad footing allowed for fire hydrant installation | 1 | item | 2347 | 2347
5 | Electrical Attendance and Builders Works | 1 | item | 5460 | 5460
0
NB - no additional traffic bollards and signage included
SUB TOTAL |  |  |  |  | 64690 | 0
NETT VARIATION COST |  |  |  |  | 64690
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 6469
VARIATION COST EXCLUDING GST |  |  |  |  | 71159
GST |  |  |  |  | 7115.9
TOTAL INCLUDING GST |  |  |  |  | 78274.9
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO2
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2025-08-13
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO2 - Upgrade to 50 dia supply Water to Ground floor
Item | Description |  |  |  | Cost | Credit
| Additional from Design to IFC from Forth Engineering | Qty | Unit | Rate ($)
1 | Upgrade to 50 dia supply Water to Ground Floor | 1 | item | 23450 | 23450
0
SUB TOTAL |  |  |  |  | 23450 | 0
NETT VARIATION COST |  |  |  |  | 23450
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 2345
VARIATION COST EXCLUDING GST |  |  |  |  | 25795
GST |  |  |  |  | 2579.5
TOTAL INCLUDING GST |  |  |  |  | 28374.5
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO3
CONTRACT VARIATION - ESTIMATE
PROJECT: | ARCO |  |  |  | Date: | 2025-08-13
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO3 - Earthworks - additional backfill & testing
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
1 | Additional backfill & testing - Latent soil conditions was so bad that new sand had to be brough in and compacted for the Pile Mat | 1 | ITEM | 69800 | 69800
0
Remove Contaminated Dirt/New Spoil/Additional Compaction
SUB TOTAL |  |  |  |  | 69800 | 0
NETT VARIATION COST |  |  |  |  | 69800
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 6980
VARIATION COST EXCLUDING GST |  |  |  |  | 76780
GST |  |  |  |  | 7678
TOTAL INCLUDING GST |  |  |  |  | 84458
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO4
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2025-08-13
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO4 - Site Amenities - Lease
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
1 | Site office land rental | 3 | Years | 100000 | 300000
0
SUB TOTAL |  |  |  |  | 300000 | 0
NETT VARIATION COST |  |  |  |  | 300000
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 30000
VARIATION COST EXCLUDING GST |  |  |  |  | 330000
GST |  |  |  |  | 33000
TOTAL INCLUDING GST |  |  |  |  | 363000
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO5
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2025-08-13
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO5 - Fire Services IFC Updates
Item | Description |  |  |  | Cost | Credit
| Additional Fire pipework required from Forth Engineering from Design to IFC | Qty | Unit | Rate ($)
1 | Fire Services Update to IFC Additional 70m 100m pipework Pump Exhaust to go from basement to roof approx. 30m 24 x new ceiling space sprinklers 34 x new exposed sprinklers 24 x car stacker heads – count as exposed similar pricing 12 water shields – count as exposed similar pricing | 1 | item | 16590 | 16590
SUB TOTAL |  |  |  |  | 16590 | 0
NETT VARIATION COST |  |  |  |  | 16590
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 1659
VARIATION COST EXCLUDING GST |  |  |  |  | 18249
GST |  |  |  |  | 1824.9
TOTAL INCLUDING GST |  |  |  |  | 20073.9
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO6
CONTRACT VARIATION - ESTIMATE
PROJECT: | ARCO |  |  |  | Date: | 2025-11-10
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO6 - Tilt up panel design from Design Development to IFC
Item | Description |  |  |  | Cost | Credit
| Revised Panel Design from Design to IFC Drawings | Qty | Unit | Rate ($)
1 | Reinforcement changes from SL102 mesh EF (S00.07 Rev A) to N12-200 EF EW (S02.00 rev 0) | 1 | item | 42780 | 42780
2 | Extra panel joints on Elevation 04 Grid 6-9 and Elevation 5 Grid G-E ( S14.01 Rev B to Rev 0) | 1 | item | included above | 0
3 | Extra small panels on Elevation 03 L01 Grid G and Elevation 5 L01 Grid G | 1 | item | included above | 0
4 | Detail change RBA16RI Spacing change from 1500mm(S00.07 Rev A) to 1000mm (S00.07 Rev 0) | 1 | item | included above | 0
5 | Remove shiplap and baffle strip | 1 | item | included above | 0
SUB TOTAL |  |  |  |  | 42780 | 0
NETT VARIATION COST |  |  |  |  | 42780
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 4278
VARIATION COST EXCLUDING GST |  |  |  |  | 47058
GST |  |  |  |  | 4705.8
TOTAL INCLUDING GST |  |  |  |  | 51763.8
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO7
CONTRACT VARIATION - ESTIMATE
PROJECT: | ARCO |  |  |  | Date: | 2025-11-11
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO7 - Panel rigging extra over from Design Development to IFC changes
Item | Description |  |  |  | Cost | Credit
| Additional Rigging and Caulking required for new Panel Design from Design to IFC | Qty | Unit | Rate ($)
1 | Panel rigging extra over due to additional panels from BP to IFC | 1 | item | 20912 | 20912
| Total panel quantity increased to 92 and panels requiring rotation with Franna has increased to 50. |  |  |  | 0
0
| Additional Fire Mastic Jointing | 1 | item | 2000 | 2000
| Additional Steel Brackets | 1 | item | 15480 | 15480
SUB TOTAL |  |  |  |  | 38392 | 0
NETT VARIATION COST |  |  |  |  | 38392
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 3839.2
VARIATION COST EXCLUDING GST |  |  |  |  | 42231.2
GST |  |  |  |  | 4223.12
TOTAL INCLUDING GST |  |  |  |  | 46454.32
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO8
CONTRACT VARIATION - ESTIMATE
PROJECT: | ARCO |  |  |  | Date: | 2026-06-14
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO8 - Additional waterproofing to lift pit and top of slab
Item | Description |  |  |  | Cost | Credit
| Updated Design from Design to IFC | Qty | Unit | Rate ($)
1 | Extend Enviro BSM waterproofing to lift pit and top of slab and upturn | 1 | item | 15175 | 15175
2 | Original Allowance - Lift pit base and walls | 1 | item | 3640 |  | 3640
SUB TOTAL |  |  |  |  | 15175 | 3640
NETT VARIATION COST |  |  |  |  | 11535
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 1153.5
VARIATION COST EXCLUDING GST |  |  |  |  | 12688.5
GST |  |  |  |  | 1268.85
TOTAL INCLUDING GST |  |  |  |  | 13957.35
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO9
CONTRACT VARIATION - ESTIMATE
PROJECT: | ARCO |  |  |  | Date: | 2026-03-06
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO9 - Electrical Design Changes from Design to IFC
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
1 |  | 1 | item | 9165 | 9165
2 | Additional EV DB B2 | 1 | item | incl | incl
3 | BWIC attendance | 1 | item | 500 | 500
SUB TOTAL |  |  |  |  | 9665 | 0
NETT VARIATION COST |  |  |  |  | 9665
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 966.5
VARIATION COST EXCLUDING GST |  |  |  |  | 10631.5
GST |  |  |  |  | 1063.15
TOTAL INCLUDING GST |  |  |  |  | 11694.65
Variation Raised By:
AC
Amy Chen
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO10
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2026-06-14
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO10 - Mechanical Design Changes Design to IFC (Provisional)
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
1 | Additional Ductwork due to clashes with Services | 1 | Item | TBA | TBA
2 | Additional Plasteboard Bulkheads | 1 | item | TBA | TBA
[5 empty] | 0 | 0
SUB TOTAL |  |  |  |  | 0 | 0
NETT VARIATION COST |  |  |  |  | 0
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 0
VARIATION COST EXCLUDING GST |  |  |  |  | 0
GST |  |  |  |  | 0
TOTAL INCLUDING GST |  |  |  |  | 0
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO11
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2026-06-14
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO11 - Extra over cost for Car Stackers Prov Sum to Updated Design
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
1 | Car Stacker price not included in original budget | 1 | item | 325000 | 325000 | 191000
2 | Builders Works/Protection/Spider Cranes | 1 | item | 20000 | 20000
Budget as per QS report no design/quote previously avaiable.
SUB TOTAL |  |  |  |  | 345000 | 191000
NETT VARIATION COST |  |  |  |  | 154000
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 15400
VARIATION COST EXCLUDING GST |  |  |  |  | 169400
GST |  |  |  |  | 16940
TOTAL INCLUDING GST |  |  |  |  | 186340
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO12
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2026-06-14
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO12 - Concrete and Reo extras from Design to IFC Drawings
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
| Additional Concrete to Footings with Design Change to Basement |  |  |  | 0
1 | Formwork |  |  |  |  | -11533
2 | Concrete Additional Changes from BP to IFC |  |  |  | 156992
3 | Reinforcement Additional supply and install |  |  |  | 41734.6
4 | Shotcrete to Walls |  |  |  | 49452.07
SUB TOTAL |  |  |  |  | 248178.67 | -11533
NETT VARIATION COST |  |  |  |  | 236645.67
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 23664.567
VARIATION COST EXCLUDING GST |  |  |  |  | 260310.237
GST |  |  |  |  | 26031.0237
TOTAL INCLUDING GST |  |  |  |  | 286341.2607
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO13
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2026-06-14
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO13 - Buildability Issue and Latent Ground Conditions
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
Latent Condition to Ground necessited Grout infill to Piles
1 | Grouting to Boundary due to Latent Condition with soil |  |  |  | 47500
2 | Omit Block Wall GL G |  |  |  | 0 | -25000
3 | Piling to GL G |  |  |  | 138000
4 | Shotcrete to Piles Wall |  |  |  | 49452
SUB TOTAL |  |  |  |  | 234952 | -25000
NETT VARIATION COST |  |  |  |  | 209952
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 20995.2
VARIATION COST EXCLUDING GST |  |  |  |  | 230947.2
GST |  |  |  |  | 23094.72
TOTAL INCLUDING GST |  |  |  |  | 254041.92
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO14
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2026-06-14
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO14 - Client Upgrade Items as per Schedule
Item | Description |  |  |  | Cost | Credit
Unit No | Upgrade cost items as per Schedule | Qty | Unit | Rate ($)
101 | Herringbone Engineered Floor Boards | 1 | ITEM | 6250 | 6250
| x2 Vertical Heated Towel Rails | 1 | ITEM | 2480 | 2480
| Feature Pendant Light (Coral Linear Rod) | 1 | ITEM | 1750 | 1750
102 | Feature Pendant Light | 1 | ITEM | 1750 | 1750
| Feature Light (Pair) | 1 | ITEM | 580 | 580
| Semi-Integrated Dishwasher | 1 | ITEM | 3450 | 3450
| Microwave | 1 | ITEM | 3649 | 3649
201 | Herringbone Engineered Floor Boards | 1 | ITEM | 6250 | 6250
| Pendant Kitchen Light | 1 | ITEM | 1750 | 1750
204 | Herringbone Engineered Floor boards | 1 | ITEM | 6250 | 6250
| Integrated Dishwasher | 1 | ITEM | 3450 | 3450
| Built-in Integrated Fridge & Freezer | 1 | ITEM | 8590 | 8590
308 | Integrated Dishwasher | 1 | ITEM | 3450 | 3450
|  | 1 | ITEM |  | 0
| Built-in Integrated Fridge & Freezer | 1 | ITEM | 8590 | 8590
| Integrated Microwave | 1 | ITEM | 3649 | 3649
402 | Herringbone Engineered Floor Boards - French Oak to Living & Kitchen | 1 | ITEM | 6250 | 6250
| Built-in Integrated Fridge & Freezer - Fisher & Paykel RS90A1 476L | 1 | ITEM | 8590 | 8590
| Feature Pendant Light - Generic | 1 | ITEM | 1750 | 1750
403 | Engineered Floor Boards | 1 | ITEM | 6250 | 6250
| Drawers | 1 | ITEM | 2750 | 2750
| Feature Pendant Light | 1 | ITEM | 1750 | 1750
404 | Integrated Dishwasher | 1 | ITEM | 3450 | 3450
| Integrated Fridge & Freezer | 1 | ITEM | 8590 | 8590
| Washing Machine | 1 | ITEM | 1649 | 1649
| x2 Heated Towel Rails | 1 | ITEM | 2480 | 2480
| Drawers | 1 | ITEM | 2750 | 2750
407 | Washing Machine | 1 | ITEM | 1649 | 1649
| Drawers | 1 | ITEM | 2750 | 2750
601 | Engineered Herringbone Floor Boards | 1 | ITEM | 6250 | 6250
| Feature Pendant Light | 1 | ITEM | 1750 | 1750
602 | Herringbone Engineered Floor Boards | 1 | ITEM | 6250 | 6250
| Integrated Dishwasher | 1 | ITEM | 3450 | 3450
| Drawers | 1 | ITEM | 2750 | 2750
| Feature Pendant Light on Kitchen Island | 1 | ITEM | 1750 | 1750
| Integrated Fridge & Freezer | 1 | ITEM | 8590 | 8590
604 | Engineered Floor Boards | 1 | ITEM | 6250 | 6250
| Drawers | 1 | ITEM | 2750 | 2750
| Vertical Heated Towel Rail | 1 | ITEM | 2480 | 2480
| Feature Pendant Light | 1 | ITEM | 1750 | 1750
704 | Integrated Dishwasher | 1 | ITEM | 3450 | 3450
| Drawers | 1 | ITEM | 2700 | 2700
| Feature Pendant Light | 1 | ITEM | 1750 | 1750
| Feature Light (Pair) | 1 | ITEM | 580 | 580
SUB TOTAL |  |  |  |  | 165046 | 0
NETT VARIATION COST |  |  |  |  | 165046
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 16504.6
VARIATION COST EXCLUDING GST |  |  |  |  | 181550.6
GST |  |  |  |  | 18155.06
TOTAL INCLUDING GST |  |  |  |  | 199705.66
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO15
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2026-06-14
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO15 - Extra over grout and reinforcememt to precat panel base 100mm
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
1 |  |  |  |  | 0
2
3
4
SUB TOTAL |  |  |  |  | 0 | 0
NETT VARIATION COST |  |  |  |  | 0
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 0
VARIATION COST EXCLUDING GST |  |  |  |  | 0
GST |  |  |  |  | 0
TOTAL INCLUDING GST |  |  |  |  | 0
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VO16
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2026-06-14
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO16 - Extra monorail on ground floor
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
1 |  |  |  |  | 0
2
3
4
SUB TOTAL |  |  |  |  | 0 | 0
NETT VARIATION COST |  |  |  |  | 0
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 0
VARIATION COST EXCLUDING GST |  |  |  |  | 0
GST |  |  |  |  | 0
TOTAL INCLUDING GST |  |  |  |  | 0
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## VOXX
CONTRACT VARIATION
PROJECT: | ARCO |  |  |  | Date: | 2026-06-14
NAME: | Welink Construction |  |  |  | Site Instruction / Ref:
SITE ADDRESS: | 22 - 24 Hood St, Subiaco
JOB No: | 1504
VO
Item | Description |  |  |  | Cost | Credit
|  | Qty | Unit | Rate ($)
1 |  |  |  |  | 0
2
3
4
SUB TOTAL |  |  |  |  | 0 | 0
NETT VARIATION COST |  |  |  |  | 0
MARGIN AND OVERHEAD COSTS (10%) |  |  |  |  | 0
VARIATION COST EXCLUDING GST |  |  |  |  | 0
GST |  |  |  |  | 0
TOTAL INCLUDING GST |  |  |  |  | 0
Variation Raised By:
AC
ACCEPTED FOR AND ON BEHALF OF CLIENT: |  |  |  |  | Authorised By:

## Register
Variation Register | [11 empty] | 2026-06-14
Job #: | 1504 |  |  | BASE CONTRACT AMOUNT |  | 28198978
Project: | ARCO |  |  | TOTAL VARIATIONS APPROVED TO DATE |  | 862182.74 | [5 empty] | Submitted
Location: | 22 - 24 Hood St, Subiaco |  |  | SUBTOTAL PSUMS TO DATE |  | 249196.2 | [5 empty] | Approved
|  |  |  | SUBTOTAL CONTRACT TO DATE |  | 29310356.94 | [5 empty] | Void
|  |  |  | PENDING |  | 361582.097 | [5 empty] | Rejected
|  |  |  | IN DISPUTE |  | 0
|  |  |  | PROJECTED CONTRACT TOTAL |  | 29671939.037
VO# | DESCRIPTION | DATE VO ISSUED | VARIATION VALUE | PENDING APPROVAL | NOT APPROVED | TOTAL APPROVED | NOT PROCEEDING | IN DISPUTE | NOD / EOT | STATUS | NOTES | Action
1 | VO1 - Wet Fire Variation to Ground Floor | 2025-08-13 | 71159 | 0 | 0 | 71159 |  |  |  | Approved | Head Contract VO | PS
2 | VO2 - Upgrade to 50 dia supply Water to Ground floor | 2025-08-13 | 25795 | 0 | 0 | 25795 |  |  |  | Approved | Head Contract VO | PS
3 | VO3 - Earthworks - additional backfill & testing | 2025-08-13 | 76780 | 0 | 0 | 76780 |  |  |  | Approved | Head Contract VO | PS
4 | VO4 - Site Amenities - Lease | 2025-08-13 | 330000 | 0 | 0 | 330000 |  |  |  | Approved | Head Contract VO | PS
5 | VO5 - Fire Services IFC Updates | 2025-08-13 | 18249 | 0 | 0 | 18249 |  |  |  | Approved | Head Contract VO | PS
6 | VO6 - Tilt up panel design from Design Development to IFC | 2025-11-10 | 47058 | 0 | 0 | 47058 |  |  |  | Approved for Signing | Head Contract VO | PS
7 | VO7 - Panel rigging extra over from Design Development to IFC changes | 2025-11-11 | 38392 | 0 | 0 | 38392 |  |  |  | Approved for Signing | Head Contract VO | PS
8 | VO8 - Additional waterproofing to lift pit and top of slab | 2025-12-02 | 12688.5 | 0 | 0 | 12688.5 |  |  |  | Approved | Head Contract VO | PS
9 | VO9 - Electrical Design Changes from Design to IFC | 2026-03-06 | 10631.5 | 10631.5 | 0 | 0 |  |  |  | Submitted | Head Contract VO
10 | VO10 - Mechanical Design Changes Design to IFC (Provisional) | 2026-03-06 | TBA | TBA | TBA | 0 |  |  |  | Submitted | Head Contract VO
11 | VO11 - Extra over cost for Car Stackers Prov Sum to Updated Design | 2026-03-06 | 169400 | 169400 | 0 | 0 |  |  |  | Submitted | Head Contract VO
12 | VO12 - Concrete and Reo extras from Design to IFC Drawings | 2026-03-06 | 260310.237 | -0.003 | 0 | 260310.24 |  |  |  | Approved | Head Contract VO | Completed works
13 | VO13 - Buildability Issue and Latent Ground Conditions | 2026-03-06 | 230947.2 | 0 | 0 | 230947.2 |  |  |  | Approved | Head Contract VO | Completed works
14 | VO14 - Client Upgrade Items as per Schedule | 2026-06-14 | 181550.6 | 181550.6 | 0 | 0 |  |  |  | Submitted | Head Contract VO
15 | VO15 - Extra over grout and reinforcememt to precat panel base 100mm | 2026-06-14 | 0 | 0 | 0 | 0 |  |  |  |  | Head Contract VO
16 | VO16 - Extra monorail on ground floor | 2026-06-14 | 0 | 0 | 0 | 0 |  |  |  |  | Head Contract VO
17
18
19
20
21
22
23
| TOTALS |  | 1472961.037 | 361582.097 | 0 | 1111378.94 | 0 | 0 |  |  | 397135.2
[11 empty] | 397135.2 | Head Contract VO
[11 empty] | 714243.74 | Client Direct VO
1111378.94
[11 empty] | 28198978 | Contract Sum
[11 empty] | 29310356.94 | Adjusted Contract Sum
[11 empty] | 29671939.037 | PROJECTED CONTRACT SUM

## Internal VO Register
Variation Register | [5 empty] | 2026-06-14
VO# | DESCRIPTION | VARIATION VALUE | BANK APPROVED | Client Approved | Pending | NOTES
1 | [6 empty] | Head Contract VO
2 | VO1 - Wet Fire Variation to Ground Floor | 71159 |  | 71159 |  |  | Client Direct VO
3 | VO2 - Upgrade to 50 dia supply Water to Ground floor | 25795 |  | 25795
4 | VO3 - Earthworks - additional backfill & testing | 76780 |  | 76780
5 | VO4 - Site Amenities - Lease | 330000 |  | 330000
6 | VO5 - Fire Services IFC Updates | 18249 |  | 18249
7 | VO6 - Tilt up panel design BP to IFC | 47058 |  | 47058
8 | VO7 - Panel rigging extra over from Design Development to IFC changes | 38392 |  | 38392
9 | VO8 - Additional waterproofing to lift pit and top of slab | 6336 |  | 6336
10 | VO9 - Electrical Design Changes from Design to IFC | 10631.5
11 | VO10 - Mechanical Design Changes Design to IFC (Provisional) | TBA
12 | VO11 - Car Stackers not included in Contract | 169400
13 | VO12 - Concrete and Reo extras from Design to IFC Drawings | 260310.24
14 | VO13 - Buildability Issue and Latent Ground Conditions | 230947.2
| TOTALS | 1285057.94 | 0 | 613769 | 0 | 613769